## Sheet1
ganttchart
|  |  |  | feb |  |  |  | march |  |  | april
section | activity | responsable | status | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8
Preliminary
| success criteria definition | all | idle
| workspace dimensions definition | all | start
| disc specifications definition | all | start
| requirements identification | umbelina | finish
| ganttchart | umbelina | start
| task repartition | umbelina | start
| camera selection | umbelina | start
| Bill of Materials | all | finish
Mechanical
body | layout definition wrt workspace | umbelina | start
| arm architecture selection | umbelina | start
| Link length calculations | umbelina | idle
| Reachability analysis | umbelina | idle
end effector | Flip mechanism concept design | max | finish
| Gripper type selection | max | finish
| gripper cad design | max | finish
| mounting cad design | max | start
fabrication | cad print | max | idle
| order parts | umbelina | idle
| assembly | umbelina | start
Electrical
Power | Power requirement calculation | nikitha | finish
| Power supply selection | nikitha | finish
Control Hardware | ESP32 configuration | nikitha | finish
| End-effector actuator driver | nikitha | start
| Sensor selection | nikitha | idle
Integration | Wiring diagram | max | idle
| Wiring | umbelina | idle
| Cable management | umbelina | idle
| Safety switch integration? | max | idle
Software
Low-Level Control | ESP32 environment setup | nikitha | finish
| Motor driver interface code | nikitha | start
| Encoder reading | nikitha | start
| Joint limit implementation? | umbelina | idle
| Motion profiling, speed? | umbelina | idle
motion | joint control (fkine) |  | idle
| Kinematics (ikine) |  | idle
| Trajectory planning |  | idle
| Pick sequence routine | umbelina | idle
| Flip sequence routine | umbelina | idle
| Place sequence routine | umbelina | idle
vision | Camera calibration | umbelina | idle
| Workspace calibration (pixel → mm transform) | umbelina | idle
| Disc detection algorithm | umbelina | idle
| Coordinate transformation to robot frame | umbelina | idle
| Single joint test |  | idle
testing
| Multi-joint coordinated motion test |  | idle
| Dry run without disc |  | idle
| Pick test |  | idle
| Flip test |  | idle
| Full pipeline test |  | idle
Validation
| Accuracy measurement | daniel | idle
| Flip success rate measurement |  | idle
| Cycle time measurement |  | idle
| System limitations analysis |  | idle
| Technical report writing |  | idle
| Code documentation repo |  | start
| CAD documentation repo |  | start
deliverables
| submission deadline |  | idle | [7 empty] | 12:00pm Monday, 13/04/2026
| oral presentation |  | idle